## Summary
Summary
Project Name | Project X
WBS Code | 123
Start Date | 2018-09-01
Key Delivery Date | 2020-01-01
Original Project Budget | 200000
Forecasted Project Cost | 249162
Project Variance | -49162
Labour to Date
Materials to Date
Spend to Date
Signed off Capex | 200000
Forecasted Capex
Capex Variance

## Resource
Resource
[11 empty] | 21 | 24 | 22 | 22 | 24 | 21 | 22 | 23 | 23 | 21 | 24 | 22 | 22
Name | Manager | Role | Team | Location | Comments | Rate | Cost Type | Total Days | Total Cost | Type | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19
Kevin McAleer |  | Project Manager | Project Team | Manchester |  | 500 | Capex | 281 | 140500 |  | 21 | 24 | 22 | 12 | 24 | 21 | 22 | 23 | 23 | 21 | 24 | 22 | 22
BA | Kevin McAleer | Business Analyst | Project Team | Manchester |  | 400 | Opex | 85 | 34000 |  | 10 | 10 | 10 | 5 | 10 | 10 | 10 | 10 | 10
Tester | Kevin McAleer | Test Analyst | Project Team | Manchester |  | 450 | Overhead | 90 | 40500 | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Total | [5 empty] | 3 |  | 456 | 215000 |  | 31 | 34 | 32 | 17 | 44 | 41 | 42 | 43 | 43 | 31 | 34 | 32 | 32

## Materials
Materials
Item | Category | Cost Type | Cost | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19
Software Licence | Software | Opex | 4662 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333
Server | Hardware | Capex | 10000 |  |  |  |  | 10000
Software Licence Year 1 | Software | Capex | 4000 | [5 empty] | 4000
Total |  |  |  | 333 | 333 | 333 | 333 | 10333 | 4333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333

## Actuals
Actuals
Actuals to Date | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19
| 1000 | 2000 | 3000 | 4000 | 4500 | 5000
Total | 1000 | 2000 | 3000 | 4000 | 4500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Lookup
Cost Type | MaterialCategories
Capex | Software
Opex | Hardware
Overhead | Consultancy
Maintenance

## Resource Costs
Resource Costs
Name | Team | Total Cost | Type | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19
Kevin McAleer | Project Team | 147000 | Capex | 10500 | 12000 | 12000 | 11000 | 11000 | 6000 | 6000 | 12000 | 12000 | 10500 | 10500 | 11000 | 11000 | 11500
BA | Project Team | 52000 | Opex | 4000 | 4000 | 4000 | 4000 | 4000 | 2000 | 2000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Tester | Project Team | 31500 | Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
Total |  |  |  | 14500 | 16000 | 16000 | 15000 | 15000 | 8000 | 8000 | 20500 | 20500 | 19000 | 19000 | 19500 | 19500 | 20000

## Forecast
Forecast
Cost | Total | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19
Resource Costs | 230500 | 14500 | 16000 | 16000 | 15000 | 15000 | 8000 | 8000 | 20500 | 20500 | 19000 | 19000 | 19500 | 19500 | 20000
Materials | 18662 | 333 | 333 | 333 | 333 | 10333 | 4333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333
Forecast | 249162 | 14833 | 16333 | 16333 | 15333 | 25333 | 12333 | 8333 | 20833 | 20833 | 19333 | 19333 | 19833 | 19833 | 20333
Cumulative Forecast |  | 14833 | 31166 | 47499 | 62832 | 88165 | 100498 | 108831 | 129664 | 150497 | 169830 | 189163 | 208996 | 228829 | 249162
Actual | 19500 | 1000 | 2000 | 3000 | 4000 | 4500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Actual |  | 1000 | 3000 | 6000 | 10000 | 14500 | 19500 | 19500 | 19500 | 3000 | 6000 | 10000 | 14500 | 19500 | 19500

## Cost Type (hidden)
Capex / Opex Breakdown
Resource
Row Labels | Sum of Sep-18 | Sum of Oct-18 | Sum of Nov-18 | Sum of Dec-18 | Sum of Jan-19 | Sum of Feb-19 | Sum of Mar-19 | Sum of Apr-19 | Sum of May-19 | Sum of Jun-19 | Sum of Jul-19 | Sum of Aug-19 | Sum of Sep-19 | Sum of Oct-19
Capex | 10500 | 12000 | 12000 | 11000 | 11000 | 6000 | 6000 | 12000 | 12000 | 10500 | 10500 | 11000 | 11000 | 11500
Opex | 4000 | 4000 | 4000 | 4000 | 4000 | 2000 | 2000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
Grand Total | 14500 | 16000 | 16000 | 15000 | 15000 | 8000 | 8000 | 20500 | 20500 | 19000 | 19000 | 19500 | 19500 | 20000
Materials
Row Labels | Sum of Sep-18 | Sum of Oct-18 | Sum of Nov-18 | Sum of Dec-18 | Sum of Jan-19 | Sum of Feb-19 | Sum of Mar-19 | Sum of Apr-19 | Sum of May-19 | Sum of Jun-19 | Sum of Jul-19 | Sum of Aug-19 | Sum of Sep-19 | Sum of Oct-19
Capex |  |  |  |  | 10000 | 4000
Opex | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333
Grand Total | 333 | 333 | 333 | 333 | 10333 | 4333 | 333 | 333 | 333 | 333 | 333 | 333 | 333 | 333
Summary
Sum of Cost
| (blank) | Capex | Opex | Overhead | Grand Total
2018
Sep | 14500 | 10500 | 4333 | 0 | 29333
Oct | 16000 | 12000 | 4333 | 0 | 32333
Nov | 16000 | 12000 | 4333 | 0 | 32333
Dec | 15000 | 11000 | 4333 | 0 | 30333
2019
Jan | 15000 | 21000 | 4333 | 0 | 40333
Feb | 8000 | 10000 | 2333 | 0 | 20333
Mar | 8000 | 6000 | 2333 | 0 | 16333
Apr | 20500 | 12000 | 4333 | 4500 | 41333
May | 20500 | 12000 | 4333 | 4500 | 41333
Jun | 19000 | 10500 | 4333 | 4500 | 38333
Jul | 19000 | 10500 | 4333 | 4500 | 38333
Aug | 19500 | 11000 | 4333 | 4500 | 39333
Sep | 19500 | 11000 | 4333 | 4500 | 39333
Oct | 20000 | 11500 | 4333 | 4500 | 40333
Grand Total | 230500 | 161000 | 56662 | 31500 | 479662

## Opex (hidden)
Sum of Cost
Opex
2018
Sep | 4333
Oct | 4333
Nov | 4333
Dec | 4333
2019
Jan | 4333
Feb | 2333
Mar | 2333
Apr | 4333
May | 4333
Jun | 4333
Jul | 4333
Aug | 4333
Sep | 4333
Oct | 4333
Grand Total | 56662
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Capex (hidden)
Sum of Cost
Capex
2018
Sep | 10500
Oct | 12000
Nov | 12000
Dec | 11000
2019
Jan | 21000
Feb | 10000
Mar | 6000
Apr | 12000
May | 12000
Jun | 10500
Jul | 10500
Aug | 11000
Sep | 11000
Oct | 11500
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.